## 1. Functional Testing
1. Functional Testing (Manual Testing)
Test Case ID | Module | Description | Test Steps | Expected Result | Actual Result | Notes | Status | Errors
TC_FUNC_ID-001 | Registration | Valid registration | Enter all valid details and submit | Account created, confirmation email sent | Account created, confirmation email sent | Email received in inbox | Fail | Fail to load the log in or sign in page
TC_FUNC_ID-002 | Registration | Existing email | Use duplicate email | Error: "Email already in use" | Error: "Invalid Sign Up" | Prevents duplicate accounts | Fail | Error message is not clear
TC_FUNC_ID-003 | Registration | Missing fields | Leave required fields empty | Error: "Field is required" | Error: "Field is required"(for Email password field) and "Invalid Sign up for others" | Highlights each missing field | Fail | Error: "Field is required"(for Email password field) and "Invalid Sign up for others"
TC_FUNC_ID-004 | Registration | Password mismatch | Enter different password & confirmation | Error: "Passwords do not match" | No Confirmation password field available | Security Issues and Forgetting of passwords amy occur | Fail | The Required field is not available
TC_FUNC_ID-005 | Login | Valid credentials | Enter correct email and password | Redirected to dashboard | Redirected to dashboard | User session started | Pass | Null
TC_FUNC_ID-006 | Login | Invalid credentials | Enter incorrect email/password | Error: "Invalid login" | Error: "Invalid login" | Works as expected with try to sign up message | Pass | Null
TC_FUNC_ID-007 | Login | Empty fields | Leave email/password empty | Validation error shown | No error shown | 400 error thrown in the console | Fail | 400 Bad Request Error thrown in the console but nothing shown in the log in page
TC_FUNC_ID-008 | Dashboard | Access after login | Login and go to dashboard | Dashboard is displayed | Dashboard is displayed | All widgets load fine | Pass | 404 error The endpoint does not exist or is misconfigured.
TC_FUNC_ID-009 | Dashboard | Access without login | Open dashboard URL directly | Redirected to login | Redirected to login | Prevents unauthorized access | Pass | Null
TC_FUNC_ID-010 | Interview Scheduling | Valid schedule | Select date/time and candidate | Interview scheduled | Interview scheduled | Email confirmation received | Pass | Null
TC_FUNC_ID-011 | Interview Scheduling | Past date | Select past date | Error: "Invalid date" | Error: "Invalid date" | Cannot schedule past dates | Pass | Null
TC_FUNC_ID-012 | Interview Scheduling | Missing candidate info | Leave fields empty | Validation error shown | Validation error shown | Input validation works | Pass | Null
TC_FUNC_ID-013 | Video Recording | Start interview | Click "Start Interview" | Camera/mic activate, recording starts | Camera/mic activate, recording starts | Prompted for permissions | Pass | Null
TC_FUNC_ID-014 | Video Recording | Submit recording | Finish and submit | Video uploaded, success message | Video uploaded, success message | Upload time acceptable | Pass | Null
TC_FUNC_ID-015 | Video Recording | Cancel interview | Click "Cancel" mid-interview | Confirmation shown, video not saved | Cancel button is not available | No data saved | Fail | Null
TC_FUNC_ID-016 | AI Feedback | Generate feedback | Submit recorded video | Feedback with score/tips shown | Not Available | Metrics & suggestions visible | Fail | Null
TC_FUNC_ID-017 | AI Feedback | No video submitted | Skip recording, request feedback | Error: "No video to analyze" | Not Available | Prevents empty feedback | Fail | Null
TC_FUNC_ID-018 | Profile | Update profile info | Edit name/photo, save | Profile updated successfully | Unable to update profile and no features to do so | Unable to update profile and no features to do so | Fail | Null
TC_FUNC_ID-019 | Profile | Change password | Enter old + new password | Password updated confirmation | Feature not available | Feature not available | Fail | Null
TC_FUNC_ID-020 | Profile | Invalid inputs | Enter invalid data (e.g., phone) | Error message shown | Feature not available | Feature not available | Fail | Null
TC_FUNC_ID-021 | Logout | Valid logout | Click "Logout" | Session ends, redirected to login | Redirected to a logout page and asks to click login button to move back to login page | Session destroyed | Fail | Null
TC_FUNC_ID-022 | Record Video | Is the button working correctly | Click on record video button | Recording Starts | Recording Starts | Used for interviews | Pass | Null
TC_FUNC_ID-023 | Permissions for Microphone and Camera | Is the permission was asked | Click on record video button | Permissions were asked | Permissions were asked | Used for privacy | Pass | Null

## 2. API TESTING
2. API TESTING (Manual Testing)
Test Case ID | Description | Method | Request Data | Expected Response | Actual Response | Status | Notes
TC_API_ID-001 | Register a new user | POST | Valid user details | 201 Created, user object returned | 404 Not Found | Fail | Check endpoint availability, request payload, or API documentation.
TC_API_ID-002 | Register with existing email | POST | Duplicate email | 409 Conflict, error message | 400 Fail to load resources | Fail | Check request format and ensure it matches API schema for duplicate email test.
TC_API_ID-003 | Login with valid credentials | POST | Valid email/password | 200 OK, token returned | 200 OK, token returned | Pass | Login successful; interview list fetched post-authentication.
TC_API_ID-004 | Login with invalid password | POST | Wrong password | 401 Unauthorized, error message | 401 Unauthorized, error message | Pass | 401 Unauthorized returned with an error message for invalid password.
TC_API_ID-005 | Get user profile | GET | Auth token in header | 200 OK, user profile JSON | 200 OK, user profile JSON | Pass | Verify endpoint availability and check the request payload or API documentation.
TC_API_ID-006 | Get profile without token | GET | No auth header | 403 Forbidden or 401 Unauthorized | 403 Forbidden or 401 Unauthorized | Pass | Ensure the request format matches the API schema, especially for duplicate email tests.
TC_API_ID-007 | Schedule interview | POST | Valid interview data | 201 Created, interview ID | 201 Created, interview ID | Pass | Ensure login is successful before fetching the interview list post-authentication.
TC_API_ID-008 | Schedule with invalid date | POST | Past date | 400 Bad Request | 400 Bad Request | Pass | 401 Unauthorized should be returned with an error message for invalid password.
TC_API_ID-009 | Get interview details | GET | Interview ID | 200 OK, interview object | 200 OK, interview object | Pass | Check that the user profile JSON is correctly returned with a 200 OK response.
TC_API_ID-010 | Get with invalid ID | GET | Non-existent ID | 404 Not Found | 404 Not Found | Pass | Ensure that a 403 Forbidden or 401 Unauthorized error is handled when access is denied.
TC_API_ID-011 | Upload interview video | POST | Video file + token | 200 OK or 201 Created | 200 OK or 201 Created | Pass | Confirm the creation of an interview ID with a 201 Created response.
TC_API_ID-012 | Upload without file | POST | No file | 400 Bad Request | 400 Bad Request | Pass | Handle invalid requests that result in a 400 Bad Request response.
TC_API_ID-013 | Generate AI feedback | GET | Interview ID | 200 OK, feedback JSON | 200 OK, feedback JSON | Pass | Make sure the interview object is returned correctly with a 200 OK response.
TC_API_ID-014 | Feedback without video | GET | ID with no recording | 400 Bad Request | 400 Bad Request | Pass | Ensure that a 404 Not Found error is returned when the resource is not found.
TC_API_ID-015 | Logout user session | POST | Valid token | 200 OK, logout success | 200 OK, logout success | Pass | Validate that feedback is submitted successfully with a 200 OK response.

## 3. UIUX TESTING
3. UI/UX TESTING (Manual Testing)
Test Case ID | Description | Test Steps | Expected Result | Actual Result | Notes | Status | Error
TC_UIUX_001 | Homepage loads correctly | Visit homepage | Logo, header, and footer visible | Loaded properly | - | Pass | -
TC_UIUX_002 | Main CTA (Get Started) visibility | View homepage | CTA button clearly visible | Visible and clickable | - | Pass | -
TC_UIUX_003 | Responsive mobile view | Resize window or test on phone | Mobile-friendly layout | Few elements overlapping | Header overlaps menu | Fail | Overlapping UI on mobile
TC_UIUX_004 | Navigation bar functionality | Click all nav links | Smooth scrolling/navigation | Links functional | - | Pass | -
TC_UIUX_005 | Form field validations | Submit form with missing fields | Show proper error messages | Generic error shown | No specific field highlighted | Fail | Poor validation feedback
TC_UIUX_006 | Color contrast accessibility | Check text-background contrast | High readability | Some gray text low contrast on white | Text harder to read in footer | Fail | Low contrast in footer
TC_UIUX_007 | Font consistency across pages | Navigate across pages | Same fonts used throughout | Consistent fonts | - | Pass | -
TC_UIUX_008 | Button hover effects | Hover over clickable buttons | Hover effects trigger | Some small buttons no hover effect | Minor buttons not animated | Fail | Missing hover animation
TC_UIUX_009 | Error message clarity (Login errors) | Try wrong login credentials | Friendly and clear error | Clear message shown | - | Pass | -
TC_UIUX_010 | Page load speed impact on UI | Open homepage and dashboard | Load under 3 seconds | ~2.2 seconds | - | Pass | -
TC_UIUX_011 | Interactive elements feedback | Click buttons, dropdowns | Immediate feedback | Button states change properly | - | Pass | -
TC_UIUX_012 | Scroll behavior | Scroll through homepage | Smooth scrolling | Smooth scroll | - | Pass | -
TC_UIUX_013 | User flow for sign-up | Complete signup flow | Smooth and intuitive | Process smooth | - | Pass | -
TC_UIUX_014 | Placement of important elements | Check button placements | Easy access to important buttons | Proper placements | - | Pass | -
TC_UIUX_015 | Consistency in icons & visuals | Check icons across pages | Consistent design | Icons match design style | - | Pass | -
TC_UIUX_016 | Check visual design consistency | Scan entire page | Consistent design | Consistent branding |  | Pass | None
TC_UIUX_017 | Check font consistency | Review fonts across pages | Same font family used | Font consistent |  | Pass | None
TC_UIUX_018 | Check color palette | Observe colors | Branding colors match | Correct palette |  | Pass | None
TC_UIUX_019 | Verify button styles | Hover on buttons | Consistent button styles | Good hover effects |  | Pass | None
TC_UIUX_020 | Check form fields styling | View signup/login forms | Fields aligned & styled | Properly aligned |  | Pass | None
TC_UIUX_021 | Mobile view rendering | Switch to mobile view | Responsive design | Mobile friendly |  | Pass | None
TC_UIUX_022 | Check image quality | Review banners, icons | High-res images | No pixelation |  | Pass | None
TC_UIUX_023 | Check page animations | Scroll through page | Smooth transitions | Animations smooth |  | Pass | None
TC_UIUX_024 | Field validation errors visible | Enter wrong inputs | Clear error messages | User-friendly errors |  | Pass | None
TC_UIUX_025 | Layout alignment | Check headers, sections | Proper alignment | Sections aligned |  | Pass | None
TC_UIUX_026 | Check for dark mode | Look for toggle | Dark mode absent | Feature not available |  | N/A | Not available

## 4. LOAD STRESS TESTING
4. LOAD STRESS TESTING
Test Case ID | Description | Test Steps | Expected Result | Actual Result | Status | Error
TC_LT_001 | Test login with 100 users simultaneously | Simulate 100 concurrent login requests | All users logged in successfully within 5 seconds | All users logged in within 4.5 seconds | Pass
TC_LT_002 | Test dashboard load with 500 users | Open dashboard simultaneously by 500 users | Dashboard loads under 8 seconds | Loaded in 7.2 seconds | Pass
TC_LT_003 | Stress test video uploads | Upload 500MB videos by 50 users concurrently | Upload completes without error | Uploads completed successfully | Pass
TC_LT_004 | Interview creation under load | Create 50 interviews simultaneously | All interviews created without error | 48 created successfully, 2 Fail | Fail | Timeout errors
TC_LT_005 | Response time test for search API | Simulate 200 searches per minute | Response time under 3 seconds | Average 2.7 seconds | Pass
TC_LT_006 | Load test for candidate report generation | Generate reports for 1000 candidates | All reports generated under 10 minutes | Completed in 9.5 minutes | Pass
TC_LT_007 | Memory usage under high traffic | Monitor memory usage at 500 concurrent users | Memory usage below 80% | Peaked at 75% | Pass
TC_LT_008 | Database connection pool exhaustion | Force 1000 DB connections | No database crashes | Stable database performance | Pass
TC_LT_009 | Continuous login/logout cycles | Automate 500 login-logout cycles | No session handling errors | All sessions handled correctly | Pass
TC_LT_010 | Interview submission under load | Submit 300 video answers simultaneously | Submissions succeed without loss | 2% submissions Fail | Fail | API throttling issue
TC_LT_011 | Test analytics dashboard with bulk data | Open dashboard with 1M records | Load within 10 seconds | Loaded in 11.5 seconds | Fail | Optimization needed
TC_LT_012 | Upload limit test | Upload files >1GB | Upload rejected with message | Upload rejected correctly | Pass
TC_LT_013 | Interview deletion under concurrent access | Delete 100 interviews at once | Deletions processed correctly | All interviews deleted | Pass
TC_LT_014 | Server CPU stress test | Increase CPU load by multiple users | CPU usage remains under 90% | Peaked at 87% | Pass
TC_LT_015 | Network bandwidth under heavy load | Simulate 10GB data upload/download | No major packet loss | Minor 0.1% packet loss | Pass

## 5. SECURITY TESTING
5. Sercurity Testing (Nikto Testing)
Test Case ID | Module | Description | Test Steps | Technical Description | Explanation | Status | Notes/Error
TC001 | Header Analysis | Retrieved x-powered-by header: PHP/8.2.27 | Send GET request to / | Server discloses PHP version in header | Revealing PHP version can aid attackers in targeting vulnerabilities | Fail | Version exposure
TC002 | Security Headers | Missing X-Frame-Options header | Send GET request to / | No X-Frame-Options header set | Site vulnerable to clickjacking attacks | Fail | Header not set
TC003 | Header Analysis | Drupal Link header found with value ARRAY(0x55e552cc8408) | Send GET request to / | Possible Drupal platform leak | May expose underlying technology to attackers | Fail | Header leak
TC004 | Header Analysis | Uncommon header 'panel' found with value 'hpanel' | Send GET request to / | Unusual header found | May reveal hosting details (hpanel: Hostinger) | Fail | Information disclosure
TC005 | Header Analysis | Uncommon header 'platform' with value 'hostinger' | Send GET request to / | Platform header exposes hosting provider | Helps attackers craft platform-specific attacks | Fail | Information disclosure
TC006 | Header Analysis | Uncommon header 'x-litespeed-cache' with value 'hit' | Send GET request to / | LiteSpeed caching identified | Minor; information disclosure | Pass | Low risk
TC007 | Header Analysis | Uncommon header 'x-turbo-charged-by' with value 'LiteSpeed' | Send GET request to / | LiteSpeed server optimization disclosed | Minor; information disclosure | Pass | Low risk
TC008 | Security Headers | Missing Strict-Transport-Security (HSTS) header | Send GET request to / | No HSTS header found | Site could be vulnerable to SSL stripping attacks | Fail | HSTS missing
TC009 | Protocols | alt-svc header found advertising HTTP/3 | Send GET request to / | HTTP/3 support advertised | Nikto cannot fully test HTTP/3 | Pass | No direct vulnerability
TC010 | Security Headers | Missing X-Content-Type-Options header | Send GET request to / | Missing header to prevent MIME-sniffing attacks | May allow content to be interpreted incorrectly | Fail | Header not set
TC011 | Header Analysis | x-litespeed-cache-control header found (public, max-age=3600) | Send GET request to /4XTkAyw3.nsconfig | Caching policy disclosed | Minor information disclosure | Pass | Low risk
TC012 | Header Analysis | x-litespeed-tag header found with cache tags | Send GET request to /4XTkAyw3.nsconfig | Cache tags exposed | Information disclosure | Pass | Low risk
TC013 | Cookie Security | Cookie elementor_split_test_client_id without HttpOnly flag | Send GET request to /4XTkAyw3.nsconfig | Cookie missing HttpOnly attribute | Vulnerable to client-side script access (XSS risk) | Fail | Cookie security flaw
TC014 | Header Analysis | x-redirect-by header found (WordPress) | Send GET request to /4XTkAyw3. | Redirect header exposing WordPress | Helps attackers identify CMS | Fail | Information disclosure

## 6. Bug Report
6. Bug Report (Manual Testing)
Bug ID | Name | Type | Page | Description | Notes
BUG-001 | Tailwind CSS used in browser build | Frontend Warning | Business Dashboard Login | Tailwind is loaded via CDN in browser build; not optimized for production. | Replace with Tailwind CLI / PostCSS / Vite plugin in production.
BUG-002 | API error - utilisation limits | Backend Error | /dashboard API | GET /api/subscription/limits/utilisation returns 500 Internal Server Error. | Server-side issue. Needs backend investigation.
BUG-003 | API error - subscription endpoint | Backend Error | /dashboard API | GET /api/subscription returns 404 Not Found. | Endpoint might be missing or deprecated.
BUG-004 | API error - organization endpoint | Backend Error | /dashboard API | GET /api/organization/organization returns 404 Not Found. | Confirm endpoint path or backend implementation.
BUG-005 | JavaScript unhandled fetch error | JS Runtime Error | Business Dashboard Login | Uncaught (in promise) error on fetch in main.59e996c2.chunk.js. | Affects dynamic loading; needs error handling in frontend.
BUG-006 | Intercom not configured | Integration Bug | Business Dashboard Login | Console shows missing App ID and disabled launcher for Intercom. | Add correct App ID and update display settings in Intercom.
BUG-007 | i18next debug logging in production | Logging Issue | Business Dashboard Login | Language debug logs appear in console (languageChanged, initialized). | Disable i18next debug logging in production environment.
BUG-008 | userLanguage API not found | Backend Error | Company Employee Dashboard | GET /api/organization/userLanguage returns 404 Not Found. | Missing or unregistered endpoint.
BUG-009 | organization/role API not found | Backend Error | Company Employee Dashboard | GET /api/organization/role returns 404 Not Found. | HR role-related data fails to load.
BUG-010 | notifications API not found | Backend Error | Company Employee Dashboard | GET /api/notifications returns 404 Not Found. | Notification section likely broken.
BUG-011 | profile settings API missing | Backend Error | Company Employee Dashboard | GET /api/settings/profile returns 404 Not Found. | Could block profile view/edit for HR.
BUG-012 | Subscription API returns 404 | Backend Error | Company Employee Dashboard | GET /api/subscription returns 404 Not Found. | Repeated across multiple pages.
BUG-013 | Utilisation limits API 500 error | Backend Error | Company Employee Dashboard | GET /api/subscription/limits/utilisation returns 500 Internal Server Error. | Same as earlier error. Suggest backend review.
BUG-014 | JS Error: Uncaught TypeError | JS Runtime Error | Company Employee Dashboard | Cannot read properties of undefined (reading 'length') in handleNotifications function. | Notifications list is undefined—check response validation.
BUG-015 | ReferenceError in Role Dispatch | JS Runtime Error | Company Employee Dashboard | An action was called but nothing was dispatched during setUserRole flow. | Likely an issue with Redux or action dispatcher misfire.
BUG-016 | i18next debug logs visible | Logging Issue | Company Employee Dashboard | languageChanged and initialized logs shown in console during HR login. | Suppress logs in production.
BUG-017 | Intercom launcher disabled | Integration Bug | Company Employee Dashboard | Intercom fails to show due to disabled launcher or missing App ID. | Reconfigure Intercom display settings.
BUG-018 | Dashboard Buttons Non-Functional & Profile Save Fails | JS Runtime Error | Business Dashboard | Buttons (Add, Edit, Save) are unresponsive; profile updates not saved. Console shows: iterable.length has been deprecated, use iterable.size or iterable.count() with stack traces referencing truncate, each, and saveProfile in chunk.js. | Likely due to outdated/incompatible Immutable.js usage. Affects global component or script.
BUG-019 | Buttons Load Indefinitely on Dashboard | Backend/API Error | Business Dashboard | Buttons respond to clicks but result in infinite loading. Console shows Tailwind CSS production warning, i18next debug logs, and multiple Fail API requests (500 and 404 errors from /subscription, /organization, etc.). | Likely caused by backend API failures and improper production configuration. Affects all users. Tailwind and i18next debug should be disabled in prod.

## 7. Compatibility Test
7. Compatibility Test (Manual Testing)
Test Case ID | Description | Test Steps | Expected Result | Actual Result | Notes | Status | Error
TC_CT_001 | Open site on Chrome (latest) | Launch interviewer.ai on Chrome | Site loads and works fine | Site loaded perfectly | - | Pass | -
TC_CT_002 | Open site on Firefox (latest) | Launch interviewer.ai on Firefox | Site loads and works fine | Site loaded properly | - | Pass | -
TC_CT_003 | Open site on Microsoft Edge | Launch interviewer.ai on Edge | Site loads and works fine | Site loaded properly | - | Pass | -
TC_CT_004 | Open site on Safari (macOS) | Launch interviewer.ai on Safari browser | Site loads and works fine | Minor CSS glitch on one button | Minor UI issue on Safari | Pass | Minor CSS misalignment
TC_CT_005 | Open site on iPhone Safari | Open interviewer.ai on iPhone | Responsive mobile view | Site was responsive | - | Pass | -
TC_CT_006 | Open site on Android Chrome | Open interviewer.ai on Android phone | Responsive mobile view | Site was responsive | - | Pass | -
TC_CT_007 | Test on older Chrome version (v90) | Launch interviewer.ai | Site loads but minor warning | Works but slower | Performance slightly slow | Pass | Minor
TC_CT_008 | Test on older Firefox version (v88) | Launch interviewer.ai | Site loads with basic functionality | Site loaded, minor UI misalignment | UI needs adjustments for old version | Pass | Minor
TC_CT_009 | Open site on 4K resolution | Test on UHD monitor | Elements scale properly | Scaled perfectly | - | Pass | -
TC_CT_010 | Open site on 1366x768 resolution | Test on low-resolution laptop | Elements adjust without overflow | Adjusted properly | - | Pass | -
TC_CT_011 | Touchscreen device compatibility | Use touchscreen to navigate site | All buttons and scrolling work | Works well | - | Pass | -
TC_CT_012 | Zoom in browser (150%) | Zoom in using browser settings | No content overlap | Layout adjusted correctly | - | Pass | -
TC_CT_013 | Zoom out browser (50%) | Zoom out using browser settings | Content should still be accessible | Accessible at smaller scale | - | Pass | -
TC_CT_014 | Test on Windows OS (10, 11) | Launch and browse | Smooth operation | No issues | - | Pass | -
TC_CT_015 | Test on macOS Ventura | Launch and browse | Smooth operation | No issues | - | Pass | -

## 8. Performance Test
8. Performance Test (LightHouse Extension from Google Chrome)
Test Case ID | Module | Type | Description | Steps | Expected Result | Actual Output | Status
TC_PERF_001 | Performance Testing | Load Testing | Test application performance with 1000 simultaneous users starting interviews | Simulate 1000 users starting interviews at the same time | System should maintain acceptable response time (<3s) | Average response time observed was 2.8 seconds, no failures | Pass
TC_PERF_002 | Performance Testing | Stress Testing | Identify maximum capacity before application crashes | Gradually increase users until the system fails | System should handle up to defined threshold without crashing | System became unresponsive at 2200 users | Pass (Limit identified)
TC_PERF_003 | Performance Testing | Spike Testing | Test sudden spike in traffic during peak hours | Simulate 500 users joining interviews in 10 seconds | System should recover quickly without errors | Minor delay (5 seconds) observed, system recovered automatically | Pass
TC_PERF_004 | Performance Testing | Endurance Testing | Check system stability over long interview sessions (6+ hours) | Conduct continuous interviews for 6 hours with users | No memory leaks or performance degradation over time | No memory leaks detected, slight increase in CPU usage (10%) | Pass
TC_PERF_005 | Performance Testing | Response Time Testing | Measure page load time for interview launch | Monitor response time for starting an interview after clicking "Start" | Page should load within 2 seconds | Average load time was 1.6 seconds | Pass
TC_PERF_006 | Performance Testing | API Load Testing | Test the performance of Interview scheduling APIs under load | Simulate 1000 API calls for scheduling at once | API should respond within SLA (Service Level Agreement) time | 95% of API responses were within 1.5 seconds | Pass
TC_PERF_007 | Performance Testing | Scalability Testing | Evaluate performance when scaling server resources | Scale servers during heavy load and monitor system behavior | Application should scale up resources efficiently | Auto-scaling triggered correctly, zero downtime | Pass
TC_PERF_008 | Performance Testing | Video Streaming Testing | Measure streaming quality under different network speeds (2G/3G/4G/WiFi) | Simulate different network environments during video interviews | Video should adapt and play without major lag | Minor buffering under 2G network, smooth on 3G/4G/WiFi | Pass
TC_PERF_009 | Performance Testing | Database Performance Testing | Measure query response time during interview evaluation (AI scoring) | Simulate bulk AI evaluations post interviews | Database should respond without timeouts or locking | Query execution time remained under 800ms | Pass
TC_PERF_010 | Performance Testing | Failover/Recovery Testing | Verify system recovery after server crash | Force shutdown a main server during active interviews | System should redirect traffic to backup server with minimal downtime | Backup server activated within 7 seconds, minimal user impact | Pass